## Slide 1: New Hanover Comprehensive Plan
Maggie Dobbs, AICP
July 10, 2019

## Slide 2: Timeline
 | 2019 |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  | 
 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Background Research |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Goals Identification |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stakeholder Interviews |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Survey |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Strategies Identification |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Workshop |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Draft Writing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Open House |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Draft Review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Adoption |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 3: Agenda
Discussion of survey questions
Review of topic: Parks and Open Space
Next steps

## Slide 4: Survey Questions
Do you feel the questions cover a broad enough range?
What other topic areas do you think are missing?
What topic areas do you feel shouldn’t be included?
Do you feel any of the questions are too leading?
Do you feel the survey will take too long to complete?
Please provide any other thoughts or feedback on the survey questions.

## Slide 5: Comp Plan Topic Schedule
2019
  May
    Preliminary issues identification
    Survey development
  June
    Housing and Population
    Survey development
  July
    Parks and open space
    Survey development
  August
    Transportation
    Survey finalization
  September (Survey launch)
    Natural and historic resources
  October
    Economic development
  November (Community Workshop)
    Workshop preparation
  December
    Future land use
2019
  January
    Community facilities and utilities
  February
    Government
  March
    Strategies development
  April
    Implementation chart development
  May (Open House)
    Open House preparation
  June
    Open House feedback review
  July – October
    Review of draft plan

## Slide 6: Values Identification
There are a number of township-owned parks throughout the township with a variety of amenities for passive and active recreation.
How do you feel about the variety of amenities offered? What should there be more/less of?
How accessible are the parks? How well do people know about them? How well are they advertised through signage or events?

## Slide 7: Values Identification
The Community Park is not centrally located per se, nor is the recreation center.
Do you wish there were a more “central” or “primary” park asset?
What balance do you want to achieve to see new parks or open spaces versus maintenance of existing amenities?

## Slide 8: Values Identification
Some privately owned open spaces and recreation areas may be under development pressure.
What would be your future goal of how to treat these properties?
Where are areas that are not preserved that should be?
How do you want the township to manage newly acquired open space?

## Slide 9: Next Steps…
Submission to PC of background materials on upcoming topics
  August: Transportation
  September: Natural and Historic resources, Survey launch
Revise survey questions for final approval at August meeting
MCPC will:
  Develop plan logo
  Create online and paper survey

## Slide 10: Questions or comments?
Maggie Dobbs, AICP
610 292-4917
mdobbs@montcopa.org